EmpowerMH — Investor Roadmap (Years 1–3)

Month 0 = Close of Current Round

## Core Thesis

Build the nation’s first of its kind and first‑call behavioral‑health ecosystem for government and enterprise by combining: (a) scaled clinical services, (b) a provider‑first marketplace, (c) SaaS case‑management for the PI ecosystem, (d) AI‑enabled healthcare‑compliance offerings, and (e) data/analytics revenue.

# Year 1 — Investor Roadmap (Months 0–12)

## 1) What We Will Prove in Year‑1

A disciplined operating system (SOPs + KPI cadence) and a fully staffed leadership spine (COO, CMO, CGO/Director of Development, CTO + 2–3 builders; CPO timing‑based).

PI/Workers’ Comp engine at meaningful throughput (targeting ~750-1,000 cases/month by Month 12) powered by dual GTM: relationships + a transparency‑forward SaaS case‑management stack with clear packaging/tiers.

Healthcare Compliance division launched by Month 12 with defined ICP, offer, ROI proof, monetization, and roll‑out plan.

Strategic VA expansion (with explicit goals/SOPs), entry into OptumServe/adjacencies, and an integrated recruiting motion.

## 2) Quarter‑by‑Quarter Plan

### Months 0–3: Lock the Operating System & Ignite GTM

### Leadership & Ops

Finalize C‑suite hires; stand up CTO + 2–3 developers (AI‑savvy); implement weekly KPI/BPR and SOP transparency across current ops.

Stand up Provider Recruiting v2 aligned to PI/WC and VA goals; define 6‑ and 12‑month accomplishments to guide resourcing.

### PI/Workers’ Comp

Complete pain‑point discovery with at least one multi‑state law firm and one multi‑state medical practice.

Lock product tiering (Core/Plus/Premium) and pricing hypotheses; start by Day 90.

### VA & Adjacent Government

Publish state‑by‑state VA expansion goals and SLAs.

Define plan to supplant pieces of incumbent workflows (e.g., scheduling/training) via process + tooling; map pathway to OptumServe growth.

### Key KPIs (exit Month 3)

Leadership seats filled; SOP library v1; ≥2 discovery partners signed (law + med).

VA expansion targets published; first 50 providers added to pipeline.

### Months 4–6: Ship the PI/WC SaaS & Prove Early Throughput

### Product & Data

Build and ship PI/WC SaaS MVP (intake → scheduling → status transparency → documentation → billing handoff).

Finalize packaging/tiers; instrument analytics for cycle‑time and satisfaction.

### Go‑to‑Market (GTM)

Convert discovery partners into Design Partners; launch 3–5 pilot firms and 3–5 pilot medical groups across multiple states.

Publish case timelines and NPS.

### VA

Implement streamlined onboarding and support systems enabling increased growth trajectory.

Advance OptumServe access; begin SOP hand‑off where we outperform incumbents.

### HCC

Define ICPs (payers, large provider groups, employers), value hypotheses, and an ROI model to test in Q3.

Draft offer narrative (reduce lost revenue and risk via behavioral‑health compliance).

Select 2–3 beta clients; define monetization (retainer + performance components).

### Key KPIs (exit Month 6)

SaaS MVP live; ≥8 PI/WC pilots; ≥250 monthly cases run‑rate.

Provider onboarding velocity ≥50/month; ≥2 HCC betas contracted.

### Months 7–9: Scale Pilots → Roll‑Out; Complete Ecosystem Build

### PI/Workers’ Comp

Complete the full PI/WC SaaS ecosystem (provider & practice portals, audit trails, referral routing, reporting).

Open controlled general availability (GA) and staff CS/implementations accordingly; publish state expansion map.

### VA

Hit mid‑year VA goals; add a second lane (new VISN/region) and demonstrate faster fill times vs. incumbents.

Advance OptumServe conversations.

### HCC

### Healthcare Compliance (HCC)

Define ICPs (payers, large provider groups, employers), value hypotheses, and an ROI model to test in Q3.

Lock ICP, offer, proof metrics, and monetization; prepare Q4 commercial roll‑out.

### Key KPIs (exit Month 9)

PI/WC SaaS ecosystem completed; ≥600 monthly cases; multi‑state coverage.

Provider network ~300 active/verified; VA SLA adherence ≥95%.

### Months 10–12: Flip to Scale & Launch Healthcare Compliance

### PI/Workers’ Comp

Ramp to ~1,000 cases/month; publish before/after metrics (cycle time, show rates, documentation completeness, client NPS).

### VA

Document measurable supplant wins; formalize OptumServe entry or a direct lane with clear milestones.

Implementation of AI-assisted exam completion protocol.

### HCC

Commercial roll‑out by Month 12 with 5–10 launch customers; marketing plan live and staffed for delivery.

### Key KPIs (exit Month 12)

PI/WC: ~750-1,000 cases/month; SaaS GA with paid tiers; ≥30 external orgs onboarded.

VA: expansion targets hit; ≥2 process‑replacement wins; OptumServe roadmap defined.

HCC: beginning paying customers; first ROI case studies in hand.

## 3) Organization & Hiring (Months 0–12)

Leadership: COO, CMO, CGO/Director of Development (from a competitor if strategic), CTO; CPO timing‑based.

Product/Engineering: 2–3 developers (AI/tooling‑oriented, builders).

GTM: PI/WC sales + implementations; marketing for PI/WC and HCC; government capture to support VA/OptumServe.

Ops: Recruiting/credentialing, scheduling, QA, compliance.

## 4) Year‑1 Seeds from Other Lines of Business

Forensic (immigration/mitigation): stand up national panel/SOPs; secure 2–3 anchor relationships; target coast‑to‑coast coverage in Year‑2.

Corrections & Re‑entry Coaching: land 1–2 pilot facilities; define curriculum delivery metrics to set up multi‑state scale in Year‑2.

Provider Marketplace & Subscriptions: quiet‑launch provider tools in Q3–Q4 to build toward paid tiers in Year‑2.

Analytics: capture data from PI/WC SaaS; publish two paid insight reports by Month 12 to validate demand for a Year‑2 analytics SKU.

## 5) Capital Use (Year‑1, High‑Level)

Build: PI/WC SaaS ecosystem; data capture; early marketplace tools.

Scale: provider recruiting/credentialing; PI/WC implementations; VA expansion; HCC delivery.

Prove: case throughput; incumbent‑replacement wins in VA; HCC ROI case studies; paying analytics pilots.

# Years 2–3 — Quarterly Roadmap

Mapping: Year 2 = Months 13–24 (Q5–Q8); Year 3 = Months 25–36 (Q9–Q12).

## Year 2 — Quarterly Roadmap

### Q5 (Months 13–15): Lock Recurring Engines

### PI / Workers’ Comp (PI/WC)

Scale from ~1,000 to 1,150–1,250 cases/month across at least 20 States.

GA Plus/Premium tiers live; 6‑week implementation playbook.

CS ratio: 1 CSM per 12 client orgs.

### SaaS (PI/WC Case‑Mgmt)

60–75 external orgs live; >85% weekly active; NRR ≥110%.

Release v2 workflow automation (status rules, SLAs, alerts).

### VA & Federal Adjacent

First‑in‑line fill automation live in ≥2 additional VISNs; time‑to‑fill reduced 20% vs Year‑1 baseline.

OptumServe/direct lane: security/vendor onboarding + first SOW.

### Healthcare Compliance (HCC)

15 paying customers; publish 2 ROI case studies.

Confirm price model (retainer + outcome kicker).

### Forensics / Corrections

Forensics: national panel ≥75 providers; 10 anchor relationships.

Corrections: 2–3 facilities live; re‑entry coaching attendance ≥80%.

### Data & Analytics

Paid Insight Report #1 shipped; 10 buyers.

Gate: Maintain gross margin trajectory while adding tiered support; if NRR <105% for SaaS, trigger adoption task force.

### Q6 (Months 16–18): Expand Coverage + Prove Multi‑Line Synergy

### PI/WC

1,250–1,350 cases/month; add 5 new states (≥30 total).

Referral API for select law‑firm networks; integrate with 2 DMS/EHRs.

### SaaS

90–100 orgs live; time‑to‑first‑value ≤14 days.

Launch admin analytics (org‑level performance dashboards).

### VA & Federal

Direct/OptumServe work in production; 95%+ SLA adherence.

Pilot cross‑training program for specialty examiners.

### HCC

25–30 paying customers; standardized implementation kit; partner with 1 payer or large employer.

### Forensics / Corrections

Forensics: nationwide coverage substantiated (all 50 states via panel/on‑demand).

Corrections: 5–6 facilities; begin outcomes tracking (disciplinary incidents, completion, post‑release engagement).

### Analytics

Insight Report #2 (outcomes correlations) + first embedded analytics SKU in SaaS Premium.

Gate: If case throughput <1,250 or SaaS orgs <90, shift SDR/CSM headcount from HCC to PI/WC for 90 days.

### Q7 (Months 19–21): Velocity & Automation

### PI/WC

1,350–1,450 cases/month; launch Rapid Response lane for urgent cases.

25% of new logos from client referrals.

### SaaS

120–130 orgs; NRR ≥115%; first network deal (10+ sites).

AI documentation assist (drafting, QC hints) in controlled rollout.

### VA & Federal

VISN coverage + one new branch/region; renewal/expansion cycle begins with performance‑based wins.

### HCC

40 customers; outcome dashboards (lost‑revenue reduction, compliance rates).

Sales‑assisted channel via 2 consulting partners.

### Forensics / Corrections

Forensics SLAs formalized; enterprise pricing.

Corrections: 8–10 facilities across ≥3 states; publish interim outcomes brief.

### Analytics

20 paid analytics customers; attach rate to SaaS Premium ≥30%.

Gate: If AI assist shows <10% cycle‑time reduction, iterate UX and prompts; hold broad rollout.

### Q8 (Months 22–24): Convert Momentum to Moat

### PI/WC

1,450–1,600 cases/month; ≥40 states active; GA for network/enterprise tier.

Formal client advisory board; quarterly release cadence locked.

### SaaS

150 orgs live; >88% weekly active users; ISO/SOC audit complete for enterprise procurement.

Self‑serve onboarding for Core tier.

### VA & Federal

Confirm category‑leading fill speed/quality metrics; bid/renewals with performance narrative.

### HCC

60 customers; first national account; gross margin ≥55% via standardized delivery.

### Forensics / Corrections

Corrections: 12–15 facilities; introduce tele‑coaching to expand capacity.

Forensics: centralized QA + testimony prep service launched.

### Analytics

$1M ARR run‑rate across insights/embedded analytics.

Gate: Board review—readiness for strategic partnerships and M&A tuck‑ins in early Year‑3.

## Year 3 — Quarterly Roadmap

### Q9 (Months 25–27): Category Leadership Push

### PI/WC

1,600–1,750 cases/month; 45+ states; enterprise SLAs with 2 national networks.

Outcome guarantees piloted (with guardrails).

### SaaS / Marketplace

180–200 orgs; >90% weekly active; NRR ≥120%.

Marketplace Provider Subscriptions v1 launched; goal: 1,000 active subscribed clinicians by Q10.

### VA & Federal

Saturation posture in current VISNs; expansion to additional branches/regions.

Automation reduces time‑to‑fill another 10%.

### HCC

80 customers; expand to employer verticals; first multi‑state health‑system logo.

### Forensics / Corrections

Corrections: 18–20 facilities; evidence‑based outcomes (attendance, completion, 3‑month post‑release engagement).

Forensics: volume pricing + national scheduling center KPI’d.

### Analytics

Embedded analytics standard in SaaS Premium; 40 paid analytics customers.

Gate: If provider subscription uptake <700 by end of Q9, ship 2 roadmap features (e.g., instant credentialing status; document templating).

### Q10 (Months 28–30): Enterprise Standardization & International Pilots

### PI/WC

1,750–1,900 cases/month; network‑health score rolled out to all clients.

Two‑way integrations with top 3 plaintiff DMS/EHRs.

### SaaS / Marketplace

220–240 orgs; in‑product referrals marketplace (controlled).

1,000–1,200 subscribed clinicians; churn ≤2%/month.

### VA & Federal

Direct awards or extended SOWs validated by performance; prepare for next‑cycle bids with published QoS.

### HCC

100+ customers; first international pilot (e.g., Canada/UK) with localized compliance modules.

### Forensics / Corrections

Corrections: 22–25 facilities; introduce staff‑training product.

Forensics: 48‑state SLA ≤10 days; expert testimony utilization increases.

### Analytics

$2–3M ARR; payer/employer channel attach rate ≥40%.

Gate: International pilot must show feasibility (regulatory, delivery, margin) within 90 days or pause.

### Q11 (Months 31–33): Scale Efficiently

### PI/WC

1,900–2,100 cases/month; satisfaction ≥90 (NPS proxy).

Regional hub model to optimize cost‑to‑serve.

### SaaS / Marketplace

260–280 orgs; Provider Subscriptions v2 (templates, QA nudges, micro‑LMS).

1,400+ subscribed clinicians; ARPU uplift via add‑ons.

### VA & Federal

Add 1–2 new geographies or service lines; publish head‑to‑head metrics vs incumbents.

### HCC

130 customers; compliance‑as‑a‑managed‑service option with tiered SLAs.

### Forensics / Corrections

Corrections: 28–30 facilities; first state‑level multi‑system agreement.

Forensics: centralized QA yields ≥15% reduction in revision cycles.

### Analytics

Cohort benchmarking product; 60+ analytics customers.

Gate: If gross margin drifts >3 pts below plan, trigger cost‑to‑serve program (automation + hub rebalancing).

### Q12 (Months 34–36): Consolidate Moat & Prep Strategic Options

### PI/WC

2,100–2,400 cases/month; 50‑state coverage; multi‑year enterprise agreements.

Demonstrated outcome‑based contracting model with risk controls.

### SaaS / Marketplace

300+ orgs; 1,800–2,000 subscribed clinicians; NRR ≥125%.

Self‑serve + partner channel repeatable; SOC2 Type II renewed.

### VA & Federal

Preferred partner posture; automated readiness reports; new branch expansion plan locked.

### HCC

160–180 customers; international pilots converted or sunset with rationale.

Case studies: denial reduction, recovered revenue, clinician compliance rates.

### Forensics / Corrections

Corrections: 35–40 facilities across ≥6 states; re‑entry outcomes white paper (with academic/policy partner).

Forensics: National brand reputation; SLAs and testimony prep differentiate.

### Analytics

$4–5M ARR; payer/employer bundles standardized.

### Employee Wellness Offering

Begin process of building out tiered offerings and pricing with potential rollout in year 4 or 5.

### Strategic Readiness (End of Year‑3)

Option A: Raise growth round for roll‑ups and international expansion.

Option B: Profitability focus with durable multi‑line ARR.

Option C: Strategic partnerships/M&A exploration (payer, network, GovCon prime).

Gate: Board offsite to pick A/B/C based on (1) recurring revenue mix (SaaS + subscriptions + analytics ≥40% of total), (2) margin profile, and (3) federal/enterprise contract durability.

## Supporting KPI Targets (Years 2–3, Roll‑Up)

Supply: Active clinicians ≥1,000 (Y2 exit) → 1,500+ (Y3 exit); subscribed clinicians 1,000–2,000 by Y3 exit.

Throughput (PI/WC): ~1,000 (Y1 exit) → 1,450–1,600 (Y2 exit) → 2,100–2,400 (Y3 exit).

SaaS Orgs: 30 (Y1 exit) → 150 (Y2 exit) → 300+ (Y3 exit); NRR ≥115% Y2, ≥120–125% Y3.

VA/Federal: SLA ≥95%; additional VISNs/branches yearly; measurable time‑to‑fill advantage vs incumbents.

HCC: 5–10 (Y1 exit) → 60 (Y2 exit) → 160–180 (Y3 exit); published ROI case studies.

Corrections: 2–3 (Q6) → 12–15 (Y2 exit) → 35–40 (Y3 exit) facilities; interim then final outcomes reports.

Analytics: $1M ARR (Y2 exit) → $4–5M ARR (Y3 exit); attach ≥40% in enterprise tiers.